## Slide 1: DATA-DRIVEN SPORTS DAY PLANNING 2024 Unilever Manufacturing Site Sports Day Prepared by: Noma Ngwane Date: August 2024

## Slide 2: KEY FINDINGS & RECOMMENDATIONS
✅ Participation Rate: 88% of workforce engaged
✅ Viable Sports: 5 out of 7 proposed
❌ Removed: Basketball & Cricket (insufficient sign-ups)
RECOMMENDED SCHEDULE:
• Football: 14 teams possible
• Netball: 20 teams possible
• Tug of War: 12 teams
• Relay: 22 teams
• Darts: Individual tournament
IMPACT: Optimised resource allocation & prevented failed activities

## Slide 3: SURVEY ANALYSIS: PARTICIPATION BREAKDOWN
KEY INSIGHTS:
• Total interest entries: 1,165
• Estimated participants: ~880 employees
• Top 3 sports: Football, Netball, Tug of War
• 2 sports removed due to minimum team requirements

## Slide 4: DECISION MODEL: SPORT VIABILITY CHECK
DECISION CRITERIA:
• Teams Possible = FLOOR(Interest / Min. Players)
• Viable if: Teams Possible ≥ 1
• Automated flagging via conditional formatting

## Slide 5: RECOMMENDED EVENT TIMELINE
TIME | ACTIVITY | LOCATION | TEAMS
09:00-10:30 | Football (Round 1) | Main Field | 7 matches
10:30-11:30 | Netball | Court 1-2 | 10 matches
11:30-12:30 | Tug of war | Field 2 | 6 matches
12:30-13:30 | LUNCH BREAK |  | 
13:30-15:00 | Football (Round 2) | Main Field | 7 matches
15:00-16:00 | Relay & Darts | Track & Hall | All participants
16:00-16:30 | AWARDS & CLOSE |  | 
RESOURCE REQUIREMENTS:
• 2 referees per team sport
• First aid station at each venue
• Water stations at all locations

## Slide 6: NEXT STEPS
1. APPROVAL REQUIRED: Final sports list & schedule
2. Budget Allocation: Based on 5 approved sports
3. Team Captains: Nominate from department leads
4. Communication: All-staff announcement (2 weeks prior)
5. Logistics: Facility booking & equipment procurement
APPROVAL:
[ ] HR Director: _______________
[ ] Site Manager: _______________
[ ] Events Lead: ________________
Timeline: 4 weeks to event day